## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
1_0 | The story of college students | As a college student with a fixed monthly allowance at the beginning of each month, who only needs to track expenses, I want my accounting software to use a deduction-based method for recording transactions, so that I can clearly see how much money I have left. | 1 | 0 | 1.Users can input their current balance on their first use and save it to a local text file. 2.Every time a new income and expenditure is added, the system automatically changes the corresponding value from the remaining amount and updates the local balance file. 3.When entering non compliant or selecting a future date for the transaction, there will be corresponding error prompts. | 2 |  | 2025.3.25 | 2025.3.26
2_0 | The story of busy professionals | As a busy professional, I want to use quick commands to record every small expense, so that I can save time to focus on more work. | 1 | 0 | 1.Users can quickly call up a mini interface or pop-up window to record expenses through keyboard shortcuts without entering the main interface. 2.Support voice command input, voice input needs to be processed locally and does not rely on cloud services. 3.The input interface only contains required fields: amount , category, and remarks. 4.Automatically fill in common categories when entering the amount. 5.Display floating notification after input completion. | 1 |  | 2025.3.25 | 2025.3.25
3_0 | The story of multi-device users | As a multi-device user, I want my accounting software to have synchronization capabilities, so that I can view or record my transactions across multiple devices simultaneously. | 1 | 0 | 1.When users add, modify, or delete transactions on one device, all devices must display completely consistent information after synchronization (manually or automatically). 2.Supports automatic synchronization (such as checking file changes every minute) and manual refresh (triggered by the "Refresh Now" button). 3.If the same transaction is modified simultaneously on multiple devices, the system needs to retain the latest version based on timestamps and prompt the user in the GUI about the occurrence and resolution of conflicts. 4.The GUI needs to display the synchronization status in real-time. | 1 |  | 2025.3.26 | 2025.3.26
4_0 | The story of laboratory researchers | As a laboratory researcher who frequently needs to purchase experimental supplies, I want my accounting software to support detailed categorization and allow unlimited custom category names, with separate statistics for each category, so that I can distinguish between my personal expenses and laboratory expenditures, and focus on the spending ratio of each part. | 1 | 0 | 1.Users can create an unlimited number of custom expense categories in the software, supporting Chinese, English, and special characters. 2.Users can edit or delete existing custom categories, and after the operation, all associated historical expenses will automatically update their classification attribution. 3.Custom category names cannot be duplicated. 4.When manually adding expenses, users need to select existing categories (including preset and custom categories) from the drop-down list. 5.The statistics module needs to independently display the total expenditure amount and proportion of each category. | 3 |  | 2025.3.27 | 2025.3.28
5_0 | The story of customizable seasonal budget adjustment for regional spending patterns | As a user in China, I want the software to have a customizable budget habit that takes into account local seasonal spending patterns like the higher expenses during the Spring Festival, so that I can better manage my finances in line with regional economic conditions and consumption habits. | 1 | 0 | 1.Customizable Seasonal Events: Users can add/delete seasonal events (such as Spring Festival and Double Eleven) in the software, and set corresponding months and expected expenditure increases (such as a 30% increase in expenditure during the Spring Festival period compared to usual). 2.Automated Budget Adjustment: The system automatically adjusts the budget ceiling for the current month based on the seasonal events set by the user, and highlights the adjusted budget allocation in the interface. 3.Local Context Integration: By default, templates for common seasonal events in China (such as Spring Festival, Mid-Autumn Festival, and National Day) are provided. Users can directly select and modify them. 4.Manual Validation: Users can manually override the budget suggestions generated by AI and view the comparative analysis before and after adjustments. 5.Error Handling: If the seasonal event time entered by the user conflicts (such as multiple events in the same month), the system needs to prompt the user to reconfigure. | 1 |  | 2025.3.28 | 2025.3.28
6_0 | The story of ai-driven budget recommendations | As a person with frugal ideas, I want AI to be able to provide me with insight into spending patterns based on my spending behavior, predict my monthly budget based on my habits, and make recommendations for specific budget allocations based on my savings goals, so I can make informed financial decisions. | 1 | 0 | 1.Spending Pattern Analysis: AI generates visualized consumption trend charts based on users' historical consumption data (at least 3 months) and tags high-frequency consumption categories (such as catering and transportation). 2.Monthly Budget Prediction: AI predicts next month's budget by distinguishing between fixed expenses (such as rent) and flexible expenses (such as entertainment), and providing a percentage recommendation for budget allocation (such as "suggest using 20% of income for savings"). 3.Savings Goal Alignment: Users can input their savings target (such as "50000 yuan in 6-month memory"), and AI will recommend monthly savings amounts based on this, and dynamically adjust budget limits for other categories. 4.Actionable Recommendations: Provide specific cost saving suggestions (such as "reducing takeaway frequency, saving 500 yuan per month"), and support users to apply this suggestion to their budget plan with just one click. 5.Manual Correction & Transparency: Users can view the logic of AI generated suggestions (such as' 10% reduction due to overspending on entertainment expenses in the past 3 months') and manually modify the recommendation values. | 4 |  | 2025.3.29 | 2025.4.1
7_0 | The story of AI-based budget planning with savings goal integration | As a consumer with a spending plan, I want the AI to automatically categorize my transactions but also allow me to verify and correct any misclassifications, so that my expense tracking is both efficient and accurate. | 1 | 0 | 1.Spending Behavior Analysis: AI generates consumption pattern reports by analyzing users' consumption data from the past 3 months (stored as CSV/JSON files), including high-frequency consumption categories (such as catering and transportation), abnormal expenditures (such as consumption exceeding the average), and trend prediction charts. 2.Monthly Budget Prediction: Based on historical data, AI forecasts the total budget of the next month, distinguishes between fixed expenses (such as rent, utilities) and adjustable expenses (such as entertainment and shopping), and provides budget allocation proportion (such as "20% of recommended savings"). 3.Savings Goal Alignment: Users can set short-term or long-term savings goals (such as "deposit 10000 yuan within 3 months"), and AI recommends monthly savings amounts based on the goals and dynamically adjusts budget limits for other categories to ensure goal achievement. 4.Actionable Recommendations: Provide specific and actionable cost saving suggestions (such as "reducing the number of takeout times per week to 2, expected to save 300 yuan per month"), and allow users to apply the suggestions to their budget plan with just one click. 5.Transparency & Manual Override: Users can view the logical explanation of the budget proposal generated by AI (such as "Due to a 10% overspending on entertainment expenses last month, the budget for this category will be reduced this month"), and support manual modification of budget allocation values. | 3 |  | 2025.4.1 | 2025.4.3
8_0 | The story of transaction data management with manual and automated entry | As a consumer who spends both online and offline, I want to be able to manually enter, automatically enter and change my transaction data, so that I can easily record all my financial activities in one place. | 1 | 0 | 1.Manual Transaction Entry: Provide a user-friendly GUI interface that supports manual input of transaction details (amount, date, category, notes) and real-time saving to a local text file (CSV/JSON format). 2.Data Modification & Deletion: Users can edit or delete entered transaction records, and the modified data needs to be synchronized and updated to a local file. An undo function is also provided to prevent accidental deletion. 3.Input Validation: Real time verification of input data (such as the amount must be a number and the date format must be YYYY-MM-DD). If there is an error, a prompt will pop up and save will be prevented. 4.Category Tagging: Support adding custom category labels for each transaction (such as "Spring Festival Red Envelope" and "Double Eleven Shopping"), and the classification information can be read by AI modules to optimize analysis results. | 2 |  | 2025.4.3 | 2025.4.4
9_0 | The story of multi-bank account holders | As a multi-bank account holder, I want to import CSV files from different banking apps into one platform, so that I can consolidate all financial data quickly. | 1 | 0 | 1.The system must support at least 3 common bank CSV format bills. 2.The system should correctly parse transaction records in CSV files with an error rate of ≤ 1%, automatically detect and prompt for duplicate transactions, and support users to manually choose to overwrite or ignore duplicate data. 3.The system should provide various error handling and feedback, such as when users provide non CSV format files or CSV file formats that are not standardized. 4.Users can upload multiple CSV files in bulk through drag and drop or file selector in the interface. After the import is completed, the interface displays the summary data within 5 seconds. | 1 |  | 2025.4.4 | 2025.4.4
10_0 | The story of novice investors | As a novice investor, I want to receive AI-generated savings recommendations aligned with my risk tolerance, so that I can confidently start building a healthy personal financial flow. | 3 | 0 | 1.Users can select risk tolerance levels (low, medium, high) through GUI interfaces such as drop-down menus or radio buttons. 2.The system needs to generate corresponding savings recommendations based on the risk level selected by the user. 3.AI needs to generate personalized recommendations based on users' transaction history data, such as monthly average expenditure, income, and savings rate. 4.If the user has not selected a risk level, the system will pop up an error prompt. 5.AI suggests saving to a local file. | 1 |  | 2025.4.5 | 2025.4.5
11_0 | The story of frequent business travelers | As a frequent business traveler, I want the AI to automatically convert and categorize foreign currency transactions, so that I can track reimbursement-eligible expenses efficiently. | 4 | 0 | 1.The system should automatically detect the type of transaction currency (such as US dollars, euros, etc.) and convert it to the local currency set by the user (such as Chinese yuan) based on real-time exchange rates. 2.The converted amount should be displayed in the transaction record and the original currency amount should be retained as a reference. 3.Exchange rate data should be obtained from reliable sources such as public APIs or manually imported exchange rate tables, and the exchange rate values and dates at the time of conversion should be recorded. 4.AI should automatically classify into preset categories based on transaction descriptions or merchant information. Users can manually adjust the classification, and the modifications need to be saved persistently. 5.Users can quickly view eligible expenses by selecting filtering options, such as' only display reimbursable transactions'. | 1 |  | 2025.4.5 | 2025.4.5
12_0 | The story of small business owners | As a small business owner, I want to compare personal and business spending through separate dashboards, so that I can maintain clear financial boundaries for tax purposes. | 2 | 0 | 1.Users can access two separate dashboards on the main interface through clear buttons or tabs, such as "Personal Expenses" and "Corporate Expenses". 2.Each dashboard only displays transaction records for the corresponding category (individual/enterprise), and is not mixed by default. 3.The system automatically classifies each transaction into either the "personal" or "business" category (based on AI classification or labels manually entered by the user). 4.When the business expense dashboard detects transactions that may involve tax deductions, the system highlights or notes them to the user. | 1 |  | 2025.4.6 | 2025.4.6
13_0 | The story of college students | As a college student, I want to track my monthly expenses, so that I can systematically monitor my daily balance and spending patterns, thereby managing my finances more effectively. | 1 | 0 | 1. The system should allow users to input and categorize monthly expenses (e.g., food, transportation, entertainment, education). 2. Users should be able to set a monthly budget for each expense category. 3. Users should receive alerts when they are approaching or exceeding their budget limits for any category. 4. The system should generate visual reports (e.g., charts, graphs) to show spending patterns over time. | 2 |  | 2025.4.5 | 2025.4.6
14_0 | The story of freelancers | As a freelancer, I want the app to automatically track my project income, categorize business-related expenses (e.g., office supplies, travel costs), and estimate quarterly tax liabilities and deductible amounts in real-time, so that I can clearly understand cash flow fluctuations and reduce financial stress. | 1 | 0 | 1. The app should connect to my payment platforms (e.g., PayPal, Stripe) to automatically record project income as it's received. 2. All business-related expenses should be automatically categorized into predefined categories (e.g., office supplies, travel, equipment) with options for manual adjustments. 3. The app should calculate estimated quarterly tax liabilities based on current income and expense data, updating in real-time as new transactions are recorded. 4. For each expense category, the app should identify and calculate deductible amounts according to relevant tax laws. 5. A visual dashboard should display daily, weekly, and monthly cash flow changes, highlighting significant fluctuations. | 4 |  | 2025.4.7 | 2025.4.10
15_0 | The story of self-employed business owners | As a self-employed business owner, I want the app to analyze industry economic trends and my cash flow data to forecast income and expenses for the coming months, so that I can optimize fund utilization during economic fluctuations, ensure business stability, and seize potential growth opportunities. | 5 | 0 | 1. The app should integrate with multiple data sources to collect industry-specific economic trend data (e.g., market research reports, industry news, economic indicators). 2. The app should provide a comprehensive dashboard displaying current economic trends relevant to the user's industry. 3. The forecasting feature should use machine learning algorithms to analyze historical data and industry trends for accurate predictions. 4. Users should receive customizable income and expense forecasts for the next 3, 6, and 12 months. 5. The app should highlight potential financial risks and opportunities based on the forecasts and current economic conditions. | 5 |  | 2025.4.10 | 2025.4.11
16_0 | The story of oversea students | As an overseas student, I want to record and manage expenses in multiple currencies, and calculate exchange rates in real-time, so that I can have a clear understanding of the financial situation during my study abroad period, optimize my budget, and reduce additional costs caused by exchange rate fluctuations. | 4 | 0 | 1.When exchange rates fluctuate significantly, the system can alert users to potential budget impacts and provide historical exchange rate trends for reference. 2.Transaction records are displayed according to currency type, and an overview page provides a summary for a clear financial picture. 3.The system supports real-time exchange rate conversion, allowing users to check current rates and automatically calculate equivalent amounts between currencies. | 1 |  | 2025.4.11 | 2025.4.11
17_0 | The story of people who need to repay loans | As a person who needs to repay a loan, I want to set repayment reminders and check interest expenses, so that I can repay on time, reduce additional interest costs, and improve my credit score. | 1 | 0 | 1.Users can set up a repayment plan on the main interface, including loan amount, repayment schedule, due dates, and preferred reminder methods such as push notifications or emails. 2.The system displays detailed breakdowns for each installment, showing the principal and interest components, and allows users to view total interest expenses. 3.As the repayment date approaches, the system sends advance reminders to prevent missed payments and avoid additional interest costs. 4.The system also provides repayment progress charts, enabling users to easily track their current repayment status and remaining balance. | 3 |  | 2025.4.11 | 2025.4.12
18_0 | The story of retired elderly persons | As a retired elderly person, I want to track my pension expenses, so that I can ensure that the funds are sufficient and arrange medical and living expenses reasonably. | 1 | 0 | 1.Users can view their pension account balance on the main interface and categorize expenses such as medical care, daily necessities, and leisure activities. 2.Users can set priority alerts for essential expenses, such as medical costs, to ensure critical needs are covered. 3.The system provides financial knowledge advice, such as how to optimize pension usage, how to avoid financial fraud, etc., to help users protect their financial security. 4.Family members or authorized caregivers can (with user consent) access spending reports to assist elderly users in financial management and provide necessary support. 5.The system supports voice input, enabling users to record expenses through speech, reducing the need for manual input. | 3 | Small user base, can be postponed | 2025.4.12 | 2025.4.15
19_0 | The story of housewife/husband | As a housewife/husband, I want to keep detailed records of various household expenses and develop monthly budgets, so that I can allocate funds reasonably, optimize savings and expenses, and ensure the long-term stability of the family's finances. | 1 | 0 | 1.Users can set savings goals, such as a home purchase fund, children’s education savings, or an emergency fund, and track their progress to support long-term financial planning. 2.With data visualization tools (such as charts and trend analysis), the system helps users easily monitor expense distribution and optimize financial allocation. 3.Users can add and categorize daily household expenses on the main interface, such as groceries, rent/mortgage, utilities, education costs, and entertainment, to gain a clear overview of spending. 4.The system enables multi-user access to household financial data, allowing spouses or family members to collaboratively manage the budget for better transparency and efficiency. | 1 |  | 2025.4.15 | 2025.4.15
20_0 | The story of student club leaders | As a student club leader, I want to keep track of the club's expenses, as well as my bank transfers from the school, and match them, so that I know if each of my expenses has been reimbursed. | 3 | 0 | 1.You can record a user's expenses and income from a specific account and match the two. 2.Allows users to add payments that need to be reimbursed and record them as reimbursed after they are matched to the reimbursement entry. 3.There is a page to contain all these functions above. | 4 |  | 2025.4.16 | 2025.4.17
21_0 | The story of leader of a short-term social practice project | As a leader of a short-term social practice project, I want like to record each of the expenses of the project members and classify them, so that I can choose the amount that can be reimbursed to the school, such as accommodation expenses, train tickets, etc., and select the amount that cannot be reimbursed to share with the project members. | 3 | 0 | 1.You can record the user's expenses and income from a specific account and match the two. 2.You can divide the record of expenses into few parts according to the class they belong to, such as accommodation fee and train tickets fee, which can be reimbursed and others such as airplan fee and meals that can not be reimbursed. 3.Allow users to manually add and categorize records. 4.Integrate functionality into the reimbursement interface. | 4 |  | 2025.4.17 | 2025.4.18
22_0 | The story of college students with part-time jobs | As a college student, I want to keep track of my part-time or internship earnings during the winter and summer holidays and choose the right way to save, so that I don't spend them all in the following semester. | 3 | 0 | 1. Record your income for a specific period of time, such as during winter and summer vacations. 2. Plan a reasonable financial plan and daily consumption plan for college students. 3. In terms of financial planning, you can merge pages with other financial related needs. | 1 |  | 2025.4.18 | 2025.4.19
23_0 | The story of student crew leaders | As a student crew leader, I want to calculate various expenses such as venue rental, equipment rental, actor and crew salaries, as well as sponsorship fees for all parties, so that the total expenditure can be kept within a reasonable range. | 5 | 0 | 1. I need a billing interface for my team that can keep track of all the expenses and sponsorships of everyone in the team. 2. I need to calculate my budget, including planned spending and available balance. 3. I also need to keep track of how the money is actually used to see if there are any unexpected expenses. | 1 | Ultra core requirement, awaiting review | 2025.4.19 | 2025.4.20
24_0 | The story of the head of a small photography studio | As a head of a small photography studio, I want to keep track of the studio's income and expenses, including the deposit and final payment for the client's shooting expenses, the cost of equipment purchases, and the salaries of assistants, so that I can understand the income and expenditure of the studio and make reasonable plans for future development. | 2 | 0 | 1. Design a bookkeeping version for a team or enterprise, count the income and expenditure of multiple people and combine them for analysis. 2. Be able to analyze the income and expenditure of enterprises, and give reasonable suggestions for enterprise development in combination with AI. | 1 |  | 2025.4.20 | 2025.4.20
1_1 | The story of college students | As a college student managing a fixed monthly allowance, I want to record transactions with a deduction-based balance display, so that I can instantly see my remaining money. | 1 | 1 | 1.Complete the acceptance criteria for user stories 1_0, 8_0, 13_0. 2.The current balance should be displayed in real-time in a prominent position (such as the top) on the GUI main interface, in the format of currency (e.g. ¥ 3000.00). 3.Users can manually input the transaction amount through the GUI and select the transaction type. 4.All transaction records must be saved to a local text file (such as CSV format). 5.The system homepage can switch between displaying the current month's balance or the current total balance. | 2 | epic1：Core Transaction Management Combined and upgraded: 1_0, 8_0,13_0 | 2025.4.22 | 2025.4.23
2_1 | The story of busy professionals | As a busy professional, I want to use voice commands or shortcuts to log small expenses, so that I can minimize time spent on manual data entry. | 1 | 1 | 1.Users can utilize voice input to quickly log small expenses with simple commands (e.g., "Lunch 50 dollars"), eliminating the need for manual entry. 2.The system provides an autocomplete feature, suggesting complete expense details based on past records when users enter partial information, speeding up the logging process. 3.The system supports smart voice recognition, automatically categorizing expenses to save users time on data organization. | 1 | epic2（Data Input Optimization） Upgraded: 2.0 | 2025.4.23 | 2025.4.23
3_1 | The story of multi-platform spenders | As a multi-platform spender (online/offline), I want to manually enter, import, or edit transactions in one interface, so that all my financial activities are centralized. | 1 | 1 | 1.Users can import multiple transactions in bulk, such as from bank accounts or e-wallets, saving time on manual data entry. 2.The system automatically recognizes and categorizes transaction types (such as online shopping, offline spending, transfers) to ensure accurate records. 3.The editing feature allows users to correct or add information to recorded transactions, ensuring financial data remains up-to-date and accurate. | 2 | epic2（Data Input Optimization） Upgraded: 8_0 | 2025.4.24 | 2025.4.25
4_1 | The story of Multi-Bank Account Users | As a multi-bank account user, I want to import CSV files from all my banking apps into a single platform, so that I can consolidate financial data without manual reconciliation. | 1 | 1 | 1.The system intelligently parses CSV file formats, recognizing transaction dates, amounts, types, and source accounts, then merges them into a unified financial view. 2.After importing transaction data, the system automatically detects and removes duplicate records to ensure accuracy. 3.Users can view all income and expenses across multiple bank accounts in a single platform, with filtering and analysis options by bank, category, or date. 4.The system provides import logs and error detection, alerting users to potential data inconsistencies or format issues, ensuring that all financial records remain complete and accurate. 5.Users can import CSV files from multiple banking apps into the system, automatically consolidating all account transactions without manual entry. | 1 | epic2（Data Input Optimization） Upgraded: 9_0 | 2025.4.25 | 2025.4.25
5_1 | The story of multi-device users | As a multi-device user, I want real-time synchronization of my financial data across all devices, so that I can view or update transactions anytime, anywhere. | 1 | 1 | 1.When users add, modify, or delete transactions on one device, all devices must display completely consistent information after synchronization (manually or automatically). 2.Supports automatic synchronization (such as checking file changes every minute) and manual refresh (triggered by the "Refresh Now" button). 3.If the same transaction is modified simultaneously on multiple devices, the system needs to retain the latest version based on timestamps and prompt the user in the GUI about the occurrence and resolution of conflicts. 4.The GUI needs to display the synchronization status in real-time. | 1 | epic3(Multi-Device Sync) Upgraded: 3_0 | 2025.4.26 | 2025.4.26
6_1 | The story of researchers managing lab and personal expenses | As a researcher managing lab and personal expenses, I want unlimited custom categories with subcategory statistics, so that I can analyze spending ratios for each project. | 1 | 1 | 1.With data analytics features, the system offers trend analysis of project expenses, helping optimize resource allocation and budget control. 2.Users can create unlimited custom spending categories and add subcategories for more detailed project expense management. 3.Spending data can be summarized by project, allowing users to view detailed expenses for each project at any time for better financial decision-making. | 3 | epic4(AI-Powered Categorization) Upgraded: 4_0 | 2025.4.27 | 2025.4.29
7_1 | The story of plan-driven consumers | As a plan-driven consumer, I want AI to auto-categorize transactions while allowing manual corrections, so that my expense tracking remains accurate and adaptable. | 1 | 1 | 1.The system automatically categorizes transaction records into appropriate spending categories using AI, ensuring accurate and efficient classification. 2.Users can manually correct AI’s categorizations within the system, offering flexibility to adjust categories based on individual spending habits and needs. 3.The AI categorization feature intelligently optimizes itself based on users’ historical records, adapting to changing spending patterns and reducing the need for manual intervention. 4.Users can customize prompts to train their AI to classify according to their own requirements and preferences. | 3 | epic4(AI-Powered Categorization) Upgraded: 7_0 | 2025.4.29 | 2025.5.3
8_1 | The story of customizable seasonal budget adjustment for regional spending patterns | As a user in China, I want customizable budgets that account for seasonal spikes (e.g., Spring Festival), so that my financial planning aligns with cultural spending patterns. | 1 | 1 | 1.Customizable Seasonal Events: Users can add/delete seasonal events (such as Spring Festival and Double Eleven) in the software, and set corresponding months and expected expenditure increases (such as a 30% increase in expenditure during the Spring Festival period compared to usual). 2.Automated Budget Adjustment: The system automatically adjusts the budget ceiling for the current month based on the seasonal events set by the user, and highlights the adjusted budget allocation in the interface. 3.Local Context Integration: By default, templates for common seasonal events in China (such as Spring Festival, Mid-Autumn Festival, and National Day) are provided. Users can directly select and modify them. 4.Manual Validation: Users can manually override the budget suggestions generated by AI and view the comparative analysis before and after adjustments. 5.Error Handling: If the seasonal event time entered by the user conflicts (such as multiple events in the same month), the system needs to prompt the user to reconfigure. | 1 | epic5(Localized Budgeting) Upgraded: 5_0 | 2025.5.3 | 2025.5.4
9_1 | The story of household managers | As a household manager, I want to create detailed family budgets with category-specific limits, so that I can optimize long-term savings and expense allocation. | 1 | 1 | 1.Users can create detailed family budgets with specific spending limits for each category (e.g., groceries, rent, utilities, education) to ensure proper fund allocation. 2.The system offers real-time budget tracking, allowing users to monitor spending progress and receive alerts if they exceed set limits. 3.Users can flexibly adjust budget limits, increasing or decreasing allocations based on monthly needs to optimize financial planning. 4.The system supports shared budget access for family members, automatically synchronizing expenses to ensure transparency in household finances. | 1 | epic5(Localized Budgeting) Upgraded: 19_0 | 2025.5.4 | 2025.5.4
10_1 | The story of frugal-minded users | As a frugal-minded user, I want AI to analyze my spending habits, predict monthly budgets, and suggest savings strategies, so that I can make informed decisions to achieve financial goals. | 1 | 1 | 1. Record and analyze past consumption habits and give financial advice. 2. Display the AI analysis results on the homepage, which is eye-catching and intuitive. 3. Access or train AI for analysis and prediction with high accuracy. | 4 | epic6(AI-Driven Insights & Predictions) Upgraded: 6_0 | 2025.5.5 | 2025.5.8
11_1 | The story of freelancers | As a freelancer, I want real-time tracking of project income, business expenses, and estimated taxes, so that I can mitigate cash flow uncertainties. | 1 | 1 | 1. Recording and analyzing irregular income and expenditure habits requires more advanced and intelligent AI. 2. Based on past data, make predictions on future income and expenditure and personal financial situation. | 4 | epic6(AI-Driven Insights & Predictions) Upgraded: 14_0 | 2025.5.8 | 2025.5.11
12_1 | The story of frequent business travelers | As a frequent business traveler, I want automatic conversion and categorization of foreign currency transactions, so that I can efficiently track reimbursable expenses. | 4 | 1 | 1. Record the time and amount of foreign currency transactions. 2. Access the real-time exchange rate of the day according to the time and calculate it to obtain the equivalent local currency amount. 3. Factor the calculation into your local currency consumption or expenditure for further analysis. | 1 | epic7(Multi-Currency & Travel Support) Upgraded: 11_0 | 2025.5.11 | 2025.5.11
13_1 | The story of International Students | As an international student, I want to manage expenses in multiple currencies with real-time exchange rates, so that I can minimize costs from currency fluctuations. | 4 | 1 | 1.Users can add and manage multiple currency accounts, supporting real-time conversions between their home currency and the local currency of their study destination. 2.Transaction records are automatically converted to the user’s chosen base currency, with comparative expense analysis between different currencies to provide clearer financial insights. 3.Users can set exchange rate alerts, receiving notifications when their target currency reaches a favorable rate, helping them choose the best time for currency exchange. | 1 | epic7(Multi-Currency & Travel Support) Upgraded: 16_0 | 2025.5.12 | 2025.5.12
14_1 | The story of small business owners | As a small business owner, I want separate dashboards for personal and business finances, so that I can maintain tax-compliant records. | 2 | 1 | 1. The system should provide two separate dashboards: one for personal finance and one for business finance to ensure a clear separation of financial data. 2. Personal dashboards should display personal income, expenditure, savings and other relevant personal financial information. 3. Enterprise dashboard should show enterprise income, expenditure, cash flow and other financial indicators related to the enterprise. 4. Users should be able to easily switch between personal and enterprise dashboards through a clear and easily accessible interface. 5. The system shall classify the entered financial transactions as personal or corporate finance according to user input. 6. The system shall implement appropriate access controls to ensure that personal and business financial data is only visible to authorized users. 7. Data entered in one dashboard should not be visible or editable in another unless explicitly shared by users. | 1 | epic8(Business Finance Tools) Upgraded: 12_0 | 2025.5.13 | 2025.5.14
15_1 | The story of photography studio owners | As a photography studio owner, I want to track income (e.g., client payments) and expenses (e.g., equipment, salaries), so that I can forecast profitability and plan expansions. | 2 | 1 | 1. The system should provide two separate dashboards: one for personal finance and one for business finance to ensure a clear separation of financial data. 2. The system shall generate monthly and annual financial reports, including income statements, cash flow analysis and balance sheets. 3. Users should be able to set financial goals within the system and track progress towards them. 4. The User shall receive reminders of insufficient cash balance and loan maturity. | 1 | epic8(Business Finance Tools) Upgraded: 24_0 | 2025.5.14 | 2025.5.15
16_1 | The story of novice investors | As a novice investor, I want risk-adjusted AI recommendations for savings and investments, so that I can build a sustainable financial portfolio. | 3 | 1 | 1. Users should be able to set risk tolerance levels (e.g., conservative, moderate, active) according to their financial situation and investment goals. 2. The AI recommendation engine should analyze the user's financial data and risk tolerance, generate personalized savings and investment recommendations and provide a clear explanation for each recommendation, including the rationale behind the suggested asset allocation. 3. Users shall periodically receive proposed updates and adjustments based on changes in their financial position or market conditions. 4. The system should allow users to adapt the AI to make better recommendations based on their own research or preferences. | 1 | epic9(Savings & Debt Management Advice) Upgraded: 10_0 | 2025.5.15 | 2025.5.16
17_1 | The story of students with seasonal income | As a student with seasonal income, I want AI to suggest savings plans for part-time earnings, so that I can avoid overspending in subsequent semesters. | 3 | 1 | 1. The system should allow users to enter details of their seasonal income, including amount, source (e.g., part-time job, internship), and time period. 2. Ai should analyze the user's income pattern and spending history to provide recommendations on how much to save. 3. The savings plan should be adjustable to allow users to set different savings goals for short-term (e.g., emergency fund) and long-term (e.g., semester expenses) goals. 4. The system should provide alerts when the user approaches the spending limit or fails to reach the savings goal. | 1 | epic9(Savings & Debt Management Advice) Upgraded: 22_0 | 2025.5.16 | 2025.5.17
18_1 | The story of student club leaders | As a student club leader, I want to match club expenses with school-funded reimbursements, so that I can ensure accountability and transparency. | 3 | 1 | 1.Complete the acceptance criteria for user stories 20_0. 2.Users can associate expenses with reimbursement records one-on-one or many to one through the interface or CSV template. 3.Indicate in the expense list whether each expense has been matched for reimbursement. 4.Indicate the expenditure details corresponding to each reimbursement in the reimbursement list. 5.Users can manually drag and drop or check to associate expenses with reimbursement records. | 4 | epic10(Reimbursement Workflows) Upgraded: 20_0 | 2025.5.17 | 2025.5.20
19_1 | The story of project leaders | As a project leader, I want to classify team expenses into reimbursable/non-reimbursable categories, so that I can allocate costs fairly between members and institutions. | 3 | 1 | 1.Complete the acceptance criteria for user stories 21_0. 2.The expense list should display the classification status (reimbursable/non reimbursable) and provide options for filtering by category (such as displaying only reimbursable items). 3.Generate a categorized summary report that displays the total reimbursable amount, non reimbursable amount, and details (such as grouping by member/institution). | 4 | epic10(Reimbursement Workflows) Upgraded: 21_0 | 2025.5.20 | 2025.5.23
20_1 | The story of loan borrowers | As a loan borrower, I want automated repayment reminders and interest cost breakdowns, so that I can avoid late fees and improve my credit score. | 1 | 1 | 1.Complete the acceptance criteria for user stories 17_0. 2.The system should send repayment reminders through in app pop-up notifications or user bound email addresses 3 days, 1 day, and the same day before the repayment date set by the user. 3.The reminder content should include the repayment amount, deadline, and consequences of overdue payments. 4.The system needs to generate repayment details for each period based on the loan type (equal principal and interest/equal principal), including the current principal to be repaid, interest, remaining principal, and total repayment amount. | 3 | epic11(Reminder & Alerts) Upgraded: 17_0 | 2025.5.23 | 2025.5.24
21_1 | The story of retirees | As a retiree managing pension funds, I want alerts for medical and living expense thresholds, so that I can ensure stable financial security. | 1 | 1 | 1.Complete the acceptance criteria for user stories 18_0. 2.Users can set custom thresholds for various fixed expenses in the system interface。 3.Users can choose monthly, quarterly, or custom time periods as threshold calculation periods. 4.The system provides suggested thresholds by default, but allows users to override them. 5.Display warning icons prominently on the homepage or financial overview page, and click to view specific overspending categories and amounts. 6.Users can choose to enable pop-up prompts or system prompt sounds. | 3 | epic11(Reminder & Alerts) Upgraded: 18_0 | 2025.5.24 | 2025.5.25
22_1 | The story of self-employed business owners | As a self-employed business owner, I want the app to analyze industry economic trends and my cash flow data to forecast income and expenses for the coming months, so that I can optimize fund utilization during economic fluctuations, ensure business stability, and seize potential growth opportunities. | 5 | 1 | 1.Complete the acceptance criteria for user stories 15_0. 2.The application must support the simultaneous import of users' cash flow data and industry economic trend data. 3.The application needs to generate revenue and expenditure forecasts for the next 3-6 months and provide the following output formats: The chart display of the predicted results should include confidence intervals or risk warnings. Text summary of key indicators. 4.The predictive model needs to combine users' historical cash flow data and industry trends, and allow users to adjust assumed parameters. 5.Users can manually correct the input parameters or misclassified data of the prediction model and regenerate the prediction. | 5 | epic12(Industry trend forecasting) Upgraded: 15_0 | 2025.5.25 | 2025.5.25